## Slide 1
THE PROCESS
Three Phases. Six Months. One Application Fully Modernized.
1
Preparation
1 Month
1 BA + 1 Architect
Signed-off tech design,
project brief, test strategy
Get it right before a single
line of code is written
2
Development
3 Months
1 BA + 2 COBOL Devs
UAT-complete code,
integration tested
1 Epic per week, 2-day sprints,
3 weeks rework buffer
3
Confirmation
2 Months
Shared team
Production cutover,
old system retired
Prove it works with real data
before anything switches off
Infosys
Confidential | February 2026

## Slide 2
PHASE 1 · PREPARATION
1 Month
1 BA + 1 Architect
Get It Right Before a Single Line of Code Is Written
1
Customize ADDI
for WCA4Z
Configure tool to fully
understand the application
2
Create Technical
Design
Aligned with SSP —
target architecture
3
Create Project
Brief
App divided into Epics
(1 Epic = 1 function)
4
Create Test
Strategy
Plus coding standards
& technical watchouts
5
AI Agents
Assist
AI helps document &
review — humans own quality
6
Review &
Sign Off
Tech Review Board +
App Owner approve
7
Convert for
AI Ingestion
Docs formatted for
AI agents in Phase 2
SIGNED
OFF
Infosys
Confidential | February 2026

## Slide 3
PHASE 2 · DEVELOPMENT SPRINTS
3 Months
1 BA + 2 COBOL Devs
One Epic Per Week. AI-Powered. Human-Validated.
1
Analyse
Business Logic
BA + Analysis Agent (WCA4Z)
creates detailed business
logic for the Epic
2
Shard into
User Stories
AI divides Epic into 10-15
self-contained stories
with success criteria
3
AI Review &
Validation
Review Agent checks every
story for completeness
and corrects issues
4
2-Day Sprint
Build & Test
Day 1: AI generates code,
devs review & unit test
Day 2: Full testing
5
UAT &
Epic Sign Off
BA drives UAT with
application owner.
Epic formally accepted.
REPEAT
WEEKLY
3-MONTH TIMELINE
E1
E2
E3
E4
E5
E6
E7
E8
E9
R1
R2
R3
Epic sprints (1 per week)
Rework & hardening
Infosys
Confidential | February 2026

## Slide 4
PHASE 3 · CONFIRMATION
2 Months
Prove It Works Before Anything Switches Off
1
Deploy with
Adapter
New system deployed alongside
prod. Both running in parallel.
2
Parallel Run
with Prod Data
Processes real prod data.
Outputs compared against
existing system.
3
Flag & Fix
Discrepancies
Every mismatch identified,
investigated, resolved.
No exceptions.
4
Cutover
After 2 months clean run —
old system off.
New takes full load.
LIVE
Infosys
Confidential | February 2026

## Slide 5
THE DIFFERENCE
Same Principles. Fundamentally Different Speed.
Orthodox Agile
AI-Powered Factory
What This Means
Sprint Length
2 weeks
2 days
5x more delivery cycles
Story Creation
BA writes manually
AI shards from Epic
Days of effort reduced to hours
Story Quality
Varies by BA
AI Review Agent validates
Consistent quality every time
Code Generation
Dev writes from scratch
AI generates, dev reviews
Dev becomes reviewer, not coder
Testing
Manual test writing
AI generates from criteria
No gap between built and tested
Documentation
Afterthought, often skipped
Generated automatically
Knowledge captured as you go
Epic Cycle
4-6 weeks
1 week
Full business function weekly
Rework
Discovered late
Caught early, fixed fast
No surprises in month 6
Traceability
Depends on discipline
Enforced in GitLab
Audit-ready from day one
Infosys
Confidential | February 2026